## Tasks and Timeline
Oder Tasks and Milestones
| Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
# | [7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Milestone 1: Conduct research to select the right tablet & vendor |  | 2021-10-24 | 2021-11-03 | 10 | bar: WEEK 1 M to WEEK 2 F
1.1 | Research tablet models |  | 2021-10-23 | 2021-10-24 | 1 | bar: WEEK 1 M
1.2 | Research Vendors |  | 2021-10-25 | 2021-10-26 | 1 | bar: WEEK 1 T
1.3 | Determine network and hard requirements with POS vendor |  | 2021-10-27 | 2021-10-29 | 2 | bar: WEEK 1 W to WEEK 1 R
1.4 | Generate quotes and review costs |  | 2021-10-30 | 2021-11-01 | 2 | bar: WEEK 1 F to WEEK 2 M
1.5 | Test tablet capabiities |  | 2021-11-02 | 2021-11-04 | 2 | bar: WEEK 2 T to WEEK 2 W
1.6 | Create contract and statement of work for vendors |  | 2021-11-05 | 2021-11-06 | 1 | bar: WEEK 2 R
1.7 | Sign contract with menu tablet supplier |  | 2021-11-07 | 2021-11-08 | 1 | bar: WEEK 2 F
2 | Milestone 2: Installation & Integration of the POS system |  |  |  | 4.5 | bar: WEEK 3 M to WEEK 3 F
2.1 | Schedule an electrician to wiring the tables |  |  |  | 0.5 | bar: WEEK 3 M
2.2 | Install tablets in the bar areas at the Downtown and North Restaurant Locations |  |  |  | 2 | bar: WEEK 3 T to WEEK 3 W
2.3 | Integrate with POS software |  |  |  | 2 | bar: WEEK 3 W to WEEK 3 R
3 | Milestone 3: Implementing Security Measures |  |  |  | 8 | bar: WEEK 4 M to WEEK 5 W
3.1 | Include payment security talking points in waitstaff training |  |  |  | 1 | bar: WEEK 4 M
3.2 | Enable GPS location services on each tablet |  |  |  | 1 | bar: WEEK 4 T
3.3 | Establishing security measures: Employee permissions |  |  |  | 2 | bar: WEEK 4 W to WEEK 4 R
3.4 | Create messaging about payment portal secuirty to display on the tablets |  |  |  | 2 | bar: WEEK 4 F to WEEK 5 M
3.5 | Create a procedure for securing tablets at the end of the night |  |  |  | 2 | bar: WEEK 5 T to WEEK 5 W
4 | Milestone 4: Staff Training |  |  |  | 13 | bar: WEEK 5 R to WEEK 8 M
4.1 | Schedule a staff meetings with GM to discuss anything that could affect waitstaff tips. |  |  |  | 1 | bar: WEEK 5 R
4.2 | Create a lauch day plan: Staff, troubleshooting, etc |  |  |  | 1 | bar: WEEK 5 F
4.3 | Schedule a training for a small group of managers, followed by waitstaff training at each location. |  |  |  | 1 | bar: WEEK 6 M
4.4 | Train the staff to update the menu |  |  |  | 10 | bar: WEEK 6 T to WEEK 8 M
5 | Milestone 5: Testing phase |  |  |  | 5 | bar: WEEK 8 T to WEEK 9 T
5.1 | Invite friends and family to do a test run of the tablets. |  |  |  | 1 | bar: WEEK 8 T
5.2 | Test run the new tablet ordering system |  |  |  | 2 | bar: WEEK 8 W to WEEK 8 R
5.3 | Implement a post-dining survey to assess customer satisfaction |  |  |  | 2 | bar: WEEK 8 F to WEEK 9 M
6 | Milestone 6: Go Live |  |  |  | 0
Formulas:
Start Date = [Due Date, row above]+[Duration]
Due Date = [Start Date]+[Duration]

## Task Brainstorm
Task Brainstorm
| Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
#
1 | Milestone 1: Conduct research to select the right tablet & vendor |  | 10 | 0.5 | 1 | 1.5
1.1 | Research tablet models |  | 1 | 0.25 | 0.5 | 1
1.2 | Research Vendors |  | 1 | 0.25 | 0.5 | 1
1.3 | Determine network and hard requirements with POS vendor |  | 2 | 2 | 4 | 4
1.4 | Generate quotes and review costs |  | 2 | 2 | 4 | 6
1.5 | Test tablet capabiities |  | 2 | 2 | 3 | 3
1.6 | Create contract and statement of work for vendors |  | 1 | 0.5 | 1 | 1.5
1.7 | Sign contract with menu tablet supplier |  | 1 | 0.5 | 0.5 | 1
2 | Milestone 2: Installation & Integration of the POS system |  | 4.5 | 3 | 5 | 8
2.1 | Schedule an electrician to wiring the tables |  | 0.5 | 1 | 1 | 2
2.2 | Install tablets in the bar areas at the Downtown and North Restaurant Locations |  | 2 | 16 | 24 | 48
2.3 | Integrate with POS software |  | 2 | 8 | 8 | 16
3 | Milestone 3: Implementing Security Measures |  | 8 | 3 | 5 | 8
3.1 | Include payment security talking points in waitstaff training |  | 1 | 2 | 2 | 4
3.2 | Enable GPS location services on each tablet |  | 1 | 2 | 2 | 4
3.3 | Establishing security measures: Employee permissions |  | 2 | 3 | 5 | 8
3.4 | Create messaging about payment portal secuirty to display on the tablets |  | 2 | 6 | 8 | 10
3.5 | Create a procedure for securing tablets at the end of the night |  | 2 | 4 | 6 | 8
4 | Milestone 4: Staff Training |  | 13 | 1.6 | 3 | 3.5
4.1 | Schedule a staff meetings with GM to discuss anything that could affect waitstaff tips. |  | 1 | 1 | 1 | 1
4.2 | Create a lauch day plan: Staff, troubleshooting, etc |  | 1 | 2 | 4 | 4
4.3 | Schedule a training for a small group of managers, followed by waitstaff training at each location. |  | 1 | 2 | 4 | 4
4.4 | Train the staff to update the menu |  | 10 | 1.2 | 2 | 3
5 | Milestone 5: Testing phase |  | 5 | 8 | 10 | 12
5.1 | Invite friends and family to do a test run of the tablets. |  | 1 | 8 | 10 | 12
5.2 | Test run the new tablet ordering system |  | 2 | 8 | 16 | 21
5.3 | Implement a post-dining survey to assess customer satisfaction |  | 2 | 2 | 2 | 4
6 | Milestone 6: Go Live

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Best POS Systems for 2021 | https://www.businessnewsdaily.com/2955-best-pos-systems.html | 24/10/2021
POS & Tablets | https://www.advantech.com/products/pos-tablets/sub_b21492fc-7a0d-4235-a398-7eb1919f6712 | 24/10/2021

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Ticket average time of eight minutes for appetizers and 12-15 minutes for entrees | Are the times set by the critieria achievable by our current kitchen staff? | Measure the ticket time for appetizer and entree | How long did it take you to receive appetizers? | Multiple choice | <5 minutes | Around 8 minutes | >12 minutes
|  |  | How long did it take you to receive entrees? | Multiple choice | <10 minutes | Around 12-15minutes | >20 minutes
|  |  | Did you use the tablet to place the orders? | Yes/No | Yes | No
A checkout time of one minute or less. | Do we have enough waiting staff to reduce checkout time? | Measure checkout time | How long didit take you to check out? | Multiple choice | 1 minute | 3 minutes | 5 minutes
|  |  | Did you use the tablet to check out? | Yes/No | Yes | No
Less than 5% of customers who use the tablets to report technical issues each week | How do we quantify what qualifies as tehcnical issues? User errors count as well? | Measure number of complaints related to tablets | Was the tablet easy to use? | Yes/No | Yes | No
|  |  | Did you run into technical issues while using the tablet? If so, please list what problems you encountered | Open-ended | Open-ended
98% order accuracy | How to separate customer order error from staff order error? | Measure number of inaccurate orders | You received all the correct orders | True/False | TRUE | FALSE
|  |  | If not, please list what order was incorrect | Open-ended | Open-ended
Average wait time of ten minutes or less before customers are seated | How about during busy time like dinner time on weekends? | Measure the waiting time of customers | How long did you wait before you were seated? | Multiple choice | <5min | Around 10 minutes | >15min
|  |  | How satisfied were you with your wait time? | Scaled | 1 (not satisfied) | 2 (decently satisfied) | 3 (very satisfied)